## UAT Dashboard
Requirements and UAT Delivery Dashboard
Employee Service Request Portal ¦ Independent portfolio case study ¦ Prepared by Gokul Raj
UAT Readiness Snapshot
Test Execution |  | Pass Rate |  | Requirements Validated | Open Sev 1–2 Defects
89.47% |  | 70.59% |  | 57.14% | 3
Execution and Defect Overview
Test Result | Count | Severity | Open Defects
Pass | 12 | Severity 1 | 0
Fail | 3 | Severity 2 | 3
Blocked | 2 | Severity 3 | 2
Not Run | 2 | Severity 4 | 1
Release Decision
Current Recommendation |  |  | NOT READY — COMPLETE OPEN EXIT CRITERIA
Portfolio disclosure: This is a simulated independent Business Analyst case study. Test outcomes, defects and dates are illustrative and are not presented as employer or client results.

## Requirements Catalog
Requirements Catalog
Employee Service Request Portal ¦ Independent Business Analyst portfolio case study
Requirement ID | Type | Requirement | Priority | Business Owner | Approval Status | Source File
FR-01 | Functional | Authenticate employees using corporate credentials | Must | Information Security | Approved | 02-business-requirements.md
FR-02 | Functional | Create a request using an approved category and subcategory | Must | Service Desk | Approved | 02-business-requirements.md
FR-03 | Functional | Require title, description, category and impact | Must | Service Desk | Approved | 02-business-requirements.md
FR-04 | Functional | Assign a unique system-generated request number | Must | Service Desk | Approved | 02-business-requirements.md
FR-05 | Functional | Route requests to a resolver group using approved category rules | Must | Service Desk | Approved | 02-business-requirements.md
FR-06 | Functional | Allow authorized agents to assign an individual resolver | Must | Service Desk | Approved | 02-business-requirements.md
FR-07 | Functional | Allow authorized users to update status and add comments | Must | Service Desk | Approved | 02-business-requirements.md
FR-08 | Functional | Allow employees to view submitted requests and current status | Must | Employee Services | Approved | 02-business-requirements.md
FR-09 | Functional | Retain user, timestamp and status history | Must | Service Desk | Approved | 02-business-requirements.md
FR-10 | Functional | Notify employees when a request is created, updated or resolved | Should | Employee Services | Approved | 02-business-requirements.md
FR-11 | Functional | Provide search and filters for applicable requests | Should | Service Desk | Approved | 02-business-requirements.md
FR-12 | Functional | Provide backlog, ageing, volume and resolution KPIs | Should | Service Desk Manager | Approved | 02-business-requirements.md
FR-13 | Functional | Allow authorized agents to reopen an eligible resolved request | Could | Service Desk | Deferred | 02-business-requirements.md
FR-14 | Functional | Allow approved attachments within the file-size limit | Could | Information Security | Deferred | 02-business-requirements.md
NFR-01 | Non-Functional | Standard pages load within three seconds under normal use | Must | IT Application Team | Approved | 02-business-requirements.md
NFR-02 | Non-Functional | Users access only requests permitted by their role | Must | Information Security | Approved | 02-business-requirements.md
NFR-03 | Non-Functional | Encrypt data in transit | Must | Information Security | Approved | 02-business-requirements.md
NFR-04 | Non-Functional | Meet applicable corporate accessibility standards | Should | Employee Services | Approved | 02-business-requirements.md
NFR-05 | Non-Functional | Retain request and audit history according to policy | Must | Information Security | Approved | 02-business-requirements.md
NFR-06 | Non-Functional | Support approved versions of major corporate browsers | Should | IT Application Team | Approved | 02-business-requirements.md
NFR-07 | Non-Functional | Show useful errors without exposing sensitive system details | Must | Information Security | Approved | 02-business-requirements.md

## RTM
Requirements Traceability Matrix
Requirement → story/rule → UAT scenario → execution result → defect traceability
Requirement | Requirement Summary | Priority | Story / Rule | UAT Scenario | Scenario Description | Result | Defect ID | Coverage Status | Traceability Notes
FR-01 | Authenticate employees | Must | Authorized access | UAT-01 | Valid employee sign-in | Pass |  | Validated | Requirement validated
FR-02 | Select active category | Must | US-01 | UAT-03 | Submit complete request | Pass |  | Validated | Requirement validated
FR-03 | Required request fields | Must | US-01 | UAT-04 | Mandatory description validation | Pass |  | Validated | Requirement validated
FR-04 | Unique request number | Must | US-01 / BR-01 | UAT-03 | Create unique request | Pass |  | Validated | Requirement validated
FR-05 | Route resolver group | Must | US-01 | UAT-05 | Category-based routing | Fail | DEF-002 | At Risk | Review linked defect
FR-06 | Assign resolver | Must | US-03 | UAT-06, UAT-07 | Valid and invalid assignment | Fail | DEF-001 | At Risk | Review linked defect
FR-07 | Update status and comments | Must | US-04, US-05 / BR-04–07 | UAT-08, UAT-09, UAT-10, UAT-11 | Status, hold, resolution and comments | Pass |  | Validated | Requirement validated
FR-08 | View submitted requests | Must | US-02 | UAT-12 | My Requests visibility | Pass |  | Validated | Requirement validated
FR-09 | Retain activity history | Must | US-03, US-04 | UAT-14 | Audit-history review | Blocked | DEF-004 | At Risk | Review linked defect
FR-10 | Send notifications | Should | US-01, US-04 | UAT-15 | Creation and resolution notifications | Fail | DEF-003 | At Risk | Review linked defect
FR-11 | Search and filter | Should | US-02 | UAT-16 | Status and date filters | Pass |  | Validated | Requirement validated
FR-12 | Manager dashboard | Should | US-06 | UAT-17, UAT-18 | Filtered KPIs and reconciliation | Blocked | DEF-005 | At Risk | Review linked defect
NFR-02 | Role-based access | Must | BR-04, BR-08 | UAT-02, UAT-13 | Restricted request and comments | Pass |  | Validated | Requirement validated
NFR-07 | Safe error messages | Must | Error-handling rule | UAT-19 | Controlled application error | Not Run |  | Pending | Execution outstanding

## UAT Tracker
UAT Execution Tracker
Editable test results with linked requirements, defects and evidence references
Scenario ID | Area | Scenario | Expected Result | Priority | Result | Tester | Execution Date | Requirement | Defect ID | Evidence | Comments
UAT-01 | Access & Security | Sign in with a valid employee account | Correct portal role is displayed | Must | Pass | Business Tester 1 | 2026-07-20 | FR-01 |  | EV-001 | Role confirmed
UAT-02 | Access & Security | Attempt to view another employee's restricted request | Access is denied without exposing data | Must | Pass | Business Tester 1 | 2026-07-20 | NFR-02 |  | EV-002 | Access denied as expected
UAT-03 | Request Submission | Submit a complete request using an active category | Unique request is created and routed | Must | Pass | Business Tester 2 | 2026-07-21 | FR-02, FR-04 |  | EV-003 | Completed
UAT-04 | Request Submission | Submit without a mandatory description | Submission is blocked with field message | Must | Pass | Business Tester 2 | 2026-07-21 | FR-03 |  | EV-004 | Validation displayed
UAT-05 | Request Submission | Submit requests for different categories | Each request reaches the correct group | Must | Fail | Business Tester 2 | 2026-07-21 | FR-05 | DEF-002 | EV-005 | Facilities request misrouted
UAT-06 | Assignment | Assign a resolver from the correct group | Assignee and history are updated | Must | Pass | Business Tester 1 | 2026-07-22 | FR-06 |  | EV-006 | Completed
UAT-07 | Assignment | Attempt assignment outside selected group | Invalid assignee cannot be saved | Must | Fail | Business Tester 1 | 2026-07-22 | FR-06 | DEF-001 | EV-007 | Unauthorized assignee saved
UAT-08 | Processing | Move Assigned request to In Progress | Transition saves with user and timestamp | Must | Pass | Business Tester 3 | 2026-07-22 | FR-07, FR-09 |  | EV-008 | Completed
UAT-09 | Processing | Place request On Hold without a reason | Update is blocked until reason entered | Must | Pass | Business Tester 3 | 2026-07-22 | FR-07 |  | EV-009 | Rule enforced
UAT-10 | Processing | Resolve without a resolution summary | Update is blocked until summary entered | Must | Pass | Business Tester 3 | 2026-07-22 | FR-07 |  | EV-010 | Rule enforced
UAT-11 | Comments | Add an internal comment | Only authorized agents see the comment | Must | Pass | Business Tester 3 | 2026-07-23 | FR-07, NFR-02 |  | EV-011 | Visibility confirmed
UAT-12 | Employee Experience | Employee opens My Requests | Only permitted requests and statuses appear | Must | Pass | Business Tester 1 | 2026-07-23 | FR-08 |  | EV-012 | Completed
UAT-13 | Employee Experience | Open a request containing internal comments | Internal comments are hidden | Must | Pass | Business Tester 1 | 2026-07-23 | NFR-02 |  | EV-013 | Completed
UAT-14 | Audit | Review request activity history | Ordered status, assignment and comments appear | Must | Blocked | Business Tester 3 | 2026-07-24 | FR-09 | DEF-004 |  | History service unavailable
UAT-15 | Notifications | Create and resolve a request | Correct notifications contain no sensitive content | Should | Fail | Business Tester 2 | 2026-07-24 | FR-10 | DEF-003 | EV-015 | Resolved notification missing
UAT-16 | Search & Filter | Filter My Requests by status and date | Results match all criteria | Should | Pass | Business Tester 2 | 2026-07-24 | FR-11 |  | EV-016 | Completed
UAT-17 | Reporting | Filter dashboard by resolver group | KPIs show only selected group | Should | Blocked | Business Tester 4 | 2026-07-25 | FR-12 | DEF-005 |  | Dashboard refresh blocked
UAT-18 | Reporting | Reconcile backlog and ageing to source requests | Dashboard matches approved calculations | Should | Not Run | Business Tester 4 |  | FR-12 |  |  | Waiting for DEF-005
UAT-19 | Errors | Trigger a controlled application error | Clear message contains no sensitive details | Must | Not Run | Business Tester 1 |  | NFR-07 |  |  | Scheduled for retest cycle

## Defect Log
UAT Defect Log
Illustrative defects demonstrate triage, traceability, ownership and release readiness
Defect ID | Title | Severity | Priority | Status | Scenario ID | Requirement | Assignee | Target Build | Due Date | Expected Result | Actual Result
DEF-001 | Resolver outside selected group can be assigned | Severity 2 | High | Ready for Retest | UAT-07 | FR-06 | Development Team | Build 1.2 | 2026-07-28 | Only members of selected resolver group can be assigned | User outside group was saved as assignee
DEF-002 | Facilities category routes to wrong resolver group | Severity 2 | High | In Progress | UAT-05 | FR-05 | Development Team | Build 1.2 | 2026-07-29 | Request routes to approved category owner | Request routed to General Service Desk
DEF-003 | Resolved notification is not generated | Severity 3 | Medium | Assigned | UAT-15 | FR-10 | Development Team | Build 1.3 | 2026-08-01 | Employee receives resolution notification | No notification was created
DEF-004 | Activity history service unavailable | Severity 2 | High | In Progress | UAT-14 | FR-09 | IT Application Team | Build 1.2 | 2026-07-29 | Authorized viewer sees ordered activity history | History page returns a service error
DEF-005 | Dashboard refresh fails for resolver filter | Severity 3 | Medium | Triaged | UAT-17 | FR-12 | BI Developer | Build 1.3 | 2026-08-02 | KPIs refresh for selected resolver group | Visuals remain blank after selection
DEF-006 | Long request title wraps unevenly | Severity 4 | Low | Deferred | UAT-12 | FR-08 | UI Developer | Backlog | 2026-08-15 | Title remains readable at supported resolution | Title overlaps status on narrow screen

## Sign-Off
UAT Sign-Off and Readiness
Formula-driven exit-criteria assessment with documented decision ownership
Exit Criteria Assessment
Criterion | Target | Current | Status | Evidence / Formula Basis | Owner
All Must-priority scenarios executed | 100% | 93.33% | Not Met | Must test execution in UAT Tracker | Business Analyst
No open Severity 1 defects | 0 | 0 | Met | Open defect count in Defect Log | QA Lead
No open Severity 2 defects | 0 | 3 | Not Met | Open defect count in Defect Log | QA Lead
Overall pass rate | ≥ 90% | 70.59% | Not Met | Passed / executed scenarios | Business Analyst
Sponsor approval recorded | Yes | No | Not Met | Formal approval record | Business Sponsor
Overall Recommendation
Current Recommendation |  | NOT READY — COMPLETE OPEN EXIT CRITERIA
Role | Name | Decision | Date | Conditions / Accepted Risks | Signature Reference
Business Sponsor | To be completed | Pending
Business Analyst | Gokul Raj | Prepared | 2026-08-03 | Independent portfolio case study
QA Lead | To be completed | Pending